## the big picture
Measure B Expenditure Plan as it Connects to the Strategic Plan
|  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
1. Crisis Residential Treatment (CRT)
Property Acquistion (CHFA Grant) |  |  |  | 500000 | 500000
Architecture and Design
Facility Planning and Progranning |  |  |  | 89000
Design, Engineering and Criteria |  |  |  | 567303
Special Consultants (Environmental/CEQA, BH Expert) |  |  |  | 58000
Geothechnical Investigation/Surveying |  |  |  | 35000
|  |  |  | subtotal > | 749303
Construction
Site Work |  |  |  | 1028214
Site work contingency (10%) |  |  |  | 102821.4
Construction |  |  | 1893714
Construction contingency (10%) |  |  | 189371.4 | [5 empty] | 189371.4
Escalation from estimate 4% @ 4 mos |  |  | 19444 | 19444
|  | 2102529.4 | < subtotal | subtotal > | 1150479.4
Build/Support
Construction Manager |  |  |  | 332000 |  | a
Construction Management Contingency @15% |  |  |  | 49800 |  | *m |  |  | 49800
Building Commissioning |  |  |  | 59167 |  | b
Materials Testing (Construction) |  |  |  | 16271 |  | c
Plan Check and Permit Fees |  |  |  | 40000 |  | d
Utility Connections |  |  |  | 50000 |  | e
Advertising, Printing and Mailing |  |  |  | 10000 |  | f
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 90000 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 100000 |  | *i |  |  |  | 2035793.4
Other CEQA cost |  |  |  | 2500 |  | *j |  |  |  | 1109971.6
City of Ukiah Address Change |  |  |  | 100 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 20000 |  | *l
Contingency (15% of Add't'l Construction costs |  |  |  | 115476 |  | g |  |  | 115476
|  |  |  | subtotal > | 885314
Cupples Bid: $3,145,765: add't'l costs resulting from this bid
Ongoing Operations
General operational costs |  |  |  | 2000000 | 2000000 |  | Up to $500,000 annual cost for 4 years | 500000
TOTAL COST BY FUNCTION: CRT |  | 2102529.4 | 2102529.4 | 5285096.4 | 5285096.4
TOTAL COST: CRT |  |  | 7387625.8
2. Other Inpatient Psychiatric Care or PHF Unit
Land acquisition |  |  |  | 500000 | 500000
Architecture and Design
Facility Planning and Progranning |  |  |  | 260000
Design, Engineering and Criteria |  |  |  | 1794959
Special Consultants (Environmental/CEQA, Behavioral Health Expert) |  |  |  | 270000
Geothechnical Investigation/Surveying |  |  |  | 60000
|  |  |  | subtotal > | 2384959
Construction
Construction |  |  | 10659000 |  |  |  | Remodel: number of beds?
Construction contingency |  |  | 1065900
|  | 11724900 | < subtotal
Build/Support
Construction Manager |  |  |  | 930031 |  | a
Construction Management Contingency @15% |  |  |  | 139504.65 |  | *m |  |  | 139505
Building Commissioning |  |  |  | 120000 |  | b
Materials Testing (Construction) |  |  |  | 93003 |  | c
Plan Check, Permit and Inspection Fees |  |  |  | 200000 |  | d
Utility Connections |  |  |  | 300000 |  | e
Advertising, Printing and Mailing |  |  |  | 5000 |  | f
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 0 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 0 |  | *i
Other CEQA cost |  |  |  | 0 |  | *j
City of Ukiah Address Change |  |  |  | 0 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 0 |  | *l
Contingency (15% of Add't'l Construction costs |  |  |  | 107700.45 |  |  |  |  | 107000
|  |  |  | subtotal > | 1895239.1
Ongoing Operations
General operational costs |  |  |  | 0 | 0 |  | Operational costs? | 0
TOTAL COST BY FUNCTION: PHF |  | 11724900 | 11724900 | 4780198.1 | 4780198.1
TOTAL COST: PHF |  |  | 16505098.1
3. Behavioral Health Regional Training Center
Property Acquisition |  |  |  | 277957 | 277957
Architecture and Design
Design/Engineering |  |  |  | 14500 | 14500
Construction/Remodel
General Remodel |  |  | 153900
Replace ceiling fans |  |  | 65520
Replace ceiling fans |  |  | 568
Fencing |  |  | 3000
Fire Sprinklers |  |  | 60000
Contingency on General Remodel only (15%) |  |  | 23085 | [5 empty] | 23085
|  | 306073 | < subtotal
Build/Support
Testing/Inspections |  |  |  | 8500
Construction Manager |  |  |  | 34753
Furnishing/Equipment |  |  |  | 3500
Other Internal Partner Fees and Overhead |  |  |  | TBD
|  |  |  | subtotal > | 46753
Ongoing Costs
Maintenance |  |  |  | 80000 |  |  |  | 20000
Landscape/Custodial |  |  |  | 33600 |  |  |  | 8400
Utilities |  |  |  | 59040 |  |  |  | 14760
Staffing (effective 2023) |  |  |  | 48000 |  |  | What purpose? | 48000
|  |  |  | subtotal > | 220640
TOTAL COST BY FUNCTION: BHRTC |  | 306073 | 306073 | 559850 | 559850
TOTAL COST: BHRTC |  |  | 865923
Crisis Stabilization Unit (CSU) |  |  | not at this time
4. Expanded outreach/ Mobile Outreach Teams
|  |  |  | 1360000 |  |  | $340,000/yr for 4 years; Location/vehicles? | 340000
Providing Services |  |  |  | 1360000 |  |  | $340,000/yr for 4 years; Vehicles/Location? | 340000
Strategic Plan: |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
TOTAL COST: MOBILE OUTREACH |  |  | 0 | 1360000
5. Expansion of Support Programs and Wellness Efforts (Community EDUCATION, Awareness, and Support (CEAS))
Providing services |  |  |  | 1400000 |  |  | $350,000/yr; Location? | 350000
TOTAL COST: CEAS |  |  | 0 | 1400000
6. Supportive Housing
Purchase/renovate for permanent housing |  |  |  | 1300000
Providing services |  |  |  | 0 |  |  | 4 year cost? Ongoing costs? | 0
TOTAL COST: SUPP. HOUSING |  |  | 0 | 1300000
7. Partial hospital care/ rehabilitative care/board and care
Providing services |  |  |  | 1040000 |  |  | $260,000/yr for 4 years; Location? | 260000
TOTAL COST: HOSPITAL CARE |  |  | 0 | 1040000
Totals for all 7 Programs: |  |  | 14133502.4 | 15725144.5 |  |  |  | 1881160 | 624237.4
Note: When the tax rate is lowered to (1/8)% after five years from (1/2)% for the first five years, this new rate will be 1/4 of the original rate. (1/8 is 1/4 of 1/2.) Thus, if we use projected annual tax proceeds of $7,250,000 , the ongoing Measure B monies would be 1/4 of this or $1,812,500 annually. This amount is close to the calculated amount of $1,881,160 in ongoing costs.
29858646.9
Additional Services/Operational Costs
Lee Kemper Report |  |  |  | 13011
Lee Kemper Report |  |  |  | 10282
Assessor Clerk Recorder - Election Costs |  |  |  | 161578
Lee Kemper Behavioral Needs Assessment |  |  |  | 14177
Sarah Riley consulting (nothing further since April of 2020) |  |  |  | 15694
Lee Kemper - Reimburse Executive Office |  |  |  | 27042
Office Expenses - Reimburse Executive Office |  |  |  | 257
CEO Labor and Benefits : X. Ung hours worked |  |  |  | 5207
Nash Gonzalez consulting |  |  |  | 8938
Verizon cell phone |  |  |  | 264
Fishman Supply Co - office supplies |  |  |  | 8
ATT Teleconference |  |  |  | 126
Laptop for Measure B |  |  |  | 1052
Measure B Salary and Benefits - A. Blair |  |  |  | 6517
Sonoma Media |  |  |  | 600
CDW GOVT and Granite Data -Pcard |  |  |  | 1214
GMR Transcription July - March 2020 |  |  |  | 1679
Facilities Salary and Benefits - Maintenance Training Ctr (in Sept 2020 exp report only) |  |  |  | 1760
Monthly Utilities - Repairs/Supplies Training Center (in Sept 2020 exp report only) |  |  |  | 1460
Measure B Salary and Benefits Alyson Bailey |  |  |  | 536000 | (4 yrs @$134K/yr)
806866
Total Allocated Measure B dollars by function: |  |  | 14133502.4 | 16532010.5
TOTAL MEASURE B DOLLARS ALLOCATED: |  |  |  | 30665512.9
|  |  | 46.09% | 53.91%
|  |  | Pct for Capital costs | Pct for Operations costs
REVENUES
|  | Maximum | Minimum
|  | 75% | 25%
TAX PROCEEDS (5 years) | Amount | Facilities | Operations
April 2018 to June 2018 | 1606571 | 1204929 | 401643
July 2018 to June 2019 | 8555373 | 6416529 | 2138843
July 2019 to June 2020 | 8647202 | 6485401 | 2161800
Projected July 2020 to June 2021
Projected July 2021 to June 2022
Projected July 2022 to March 2023
18809146
Quarterly Interest
Year 1 | 52500
Year 2 | 150000
Year 3 | 150000
Year 4 | 112500
Year 5 | 75000
540000
CHFA Grant | 500000 | [5 empty] | 38685146
777500
Annual Facilities Revenue | [6 empty] | 500000
Year 1 | 6052500 | [5 empty] | 345808
Year 2 | 6525000
Year 3 | 5900000 | [5 empty] | +
Year 4 | 5550000 | [5 empty] | 40308454
Year 5 | 7000000
31027500
| 17-18 actual (Apr-Jun ONLY) | 18-19 actual Year 1 (Jul-Jun) | 19-20 actual Year 2 (Jul-Jun) | 20-21 projected Year 3 (Jul-Jun) | 21-22 projected Year 4 (Jul-Jun) | 22-23 projected Year 5 Jul - Mar ONLY
TAX PROCEEDS (5 years) | 1606571 | 8555373 | 8647202 | 7000000 | 7251000 | 5625000
Quarterly Interest | 52500 | 150000 | 150000 | 200000 | 150000 | 75000
CHFA Grant |  |  | 500000
BHRTC Rental |  |  | 48448 | 73920 | 104160 | 119280
| 1659071 | 8705373 | 9345650 | 7273920 | 7505160 | 5819280
+
40308454
TOTAL MEASURE B EXPENSES ALLOCATED: | -30665512.9
TOTAL MEASURE B REVENUES: | 40308454
PROJECTED MEASURE B DOLLARS STILL AVAILABLE: | 9642941.1
Note: According to this financial analysis, a projected balance of $8,532,970 in Measure B dollars remains. The committee could consider building a second Crisis Residential Treatment facility in Ft. Bragg with this balance. According to the above figures, the total cost for a CRT is $7,387,626. This includes general operational costs for the next four years. There are options for a CRT that could be considered other than acquiring property and building from the ground up that could be less costly.

## Sheet1
Measure B Expenditure Plan as it Connects to the Strategic Plan
|  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
1. Crisis Residential Treatment (CRT)
Property Acquistion (CHFA Grant) |  |  |  | 500000 | 500000
Architecture and Design
Facility Planning and Progranning |  |  |  | 89000
Design, Engineering and Criteria |  |  |  | 567303
Special Consultants (Environmental/CEQA, BH Expert) |  |  |  | 58000
Geothechnical Investigation/Surveying |  |  |  | 35000
|  |  |  | subtotal > | 749303
Construction
Site Work |  |  |  | 1028214
Site work contingency (10%) |  |  |  | 102821.4
Construction |  |  | 1893714
Construction contingency (10%) |  |  | 189371.4 | [5 empty] | 189371.4
Escalation from estimate 4% @ 4 mos |  |  | 19444 | 19444
|  | 2102529.4 | < subtotal | subtotal > | 1150479.4
Build/Support
Construction Manager |  |  |  | 332000 |  | a
Construction Management Contingency @15% |  |  |  | 49800 |  | *m |  |  | 49800
Building Commissioning |  |  |  | 59167 |  | b
Materials Testing (Construction) |  |  |  | 16271 |  | c
Plan Check and Permit Fees |  |  |  | 40000 |  | d
Utility Connections |  |  |  | 50000 |  | e
Advertising, Printing and Mailing |  |  |  | 10000 |  | f
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 90000 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 100000 |  | *i
Other CEQA cost |  |  |  | 2500 |  | *j
City of Ukiah Address Change |  |  |  | 100 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 20000 |  | *l
Contingency (15% of Add't'l Construction costs |  |  |  | 115476 |  | g |  |  | 115476
|  |  |  | subtotal > | 885314
Ongoing Operations
General operational costs |  |  |  | 2000000 | 2000000 |  | Up to $500,000 annual cost for 4 years | 500000
TOTAL COST BY FUNCTION: CRT |  | 2102529.4 | 2102529.4 | 5285096.4 | 5285096.4
TOTAL COST: CRT |  |  | 7387625.8
2. Other Inpatient Psychiatric Care or PHF Unit
Land acquisition |  |  |  | 500000 | 500000
Architecture and Design
Facility Planning and Progranning |  |  |  | 260000
Design, Engineering and Criteria |  |  |  | 1794959
Special Consultants (Environmental/CEQA, Behavioral Health Expert) |  |  |  | 270000
Geothechnical Investigation/Surveying |  |  |  | 60000
|  |  |  | subtotal > | 2384959
Construction
Construction |  |  | 10659000 |  |  |  | Remodel: number of beds?
Construction contingency |  |  | 1065900
|  | 11724900 | < subtotal
Build/Support
Construction Manager |  |  |  | 930031 |  | a
Construction Management Contingency @15% |  |  |  | 139504.65 |  | *m |  |  | 139505
Building Commissioning |  |  |  | 120000 |  | b
Materials Testing (Construction) |  |  |  | 93003 |  | c
Plan Check, Permit and Inspection Fees |  |  |  | 200000 |  | d
Utility Connections |  |  |  | 300000 |  | e
Advertising, Printing and Mailing |  |  |  | 5000 |  | f
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 0 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 0 |  | *i
Other CEQA cost |  |  |  | 0 |  | *j
City of Ukiah Address Change |  |  |  | 0 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 0 |  | *l
Contingency (15% of Add't'l Construction costs |  |  |  | 107700.45 |  |  |  |  | 107000
|  |  |  | subtotal > | 1895239.1
Ongoing Operations
General operational costs |  |  |  | 0 | 0 |  | Operational costs? | 0
TOTAL COST BY FUNCTION: PHF |  | 11724900 | 11724900 | 4780198.1 | 4780198.1
TOTAL COST: PHF |  |  | 16505098.1
3. Behavioral Health Regional Training Center
Property Acquisition |  |  |  | 277957 | 277957
Architecture and Design
Design/Engineering |  |  |  | 14500 | 14500
Construction/Remodel
General Remodel |  |  | 153900
Replace ceiling fans |  |  | 65520
Replace ceiling fans |  |  | 568
Fencing |  |  | 3000
Fire Sprinklers |  |  | 60000
Contingency on General Remodel only (15%) |  |  | 23085 | [5 empty] | 23085
|  | 306073 | < subtotal
Build/Support
Testing/Inspections |  |  |  | 8500
Construction Manager |  |  |  | 34753
Furnishing/Equipment |  |  |  | 3500
Other Internal Partner Fees and Overhead |  |  |  | TBD
|  |  |  | subtotal > | 46753
Ongoing Costs
Maintenance |  |  |  | 80000 |  |  |  | 20000
Landscape/Custodial |  |  |  | 33600 |  |  |  | 8400
Utilities |  |  |  | 59040 |  |  |  | 14760
Staffing (effective 2023) |  |  |  | 48000 |  |  | What purpose? | 48000
|  |  |  | subtotal > | 220640
TOTAL COST BY FUNCTION: BHRTC |  | 306073 | 306073 | 559850 | 559850
TOTAL COST: BHRTC |  |  | 865923
Crisis Stabilization Unit (CSU) |  |  | not at this time
4. Expanded outreach/ Mobile Outreach Teams
|  |  |  | 1360000 |  |  | $340,000/yr for 4 years; Location/vehicles? | 340000
Providing Services |  |  |  | 1360000 |  |  | $340,000/yr for 4 years; Vehicles/Location? | 340000
Strategic Plan: |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
TOTAL COST: MOBILE OUTREACH |  |  | 0 | 1360000
5. Expansion of Support Programs and Wellness Efforts (Community Education, Awareness, and Support (CEAS))
Providing services |  |  |  | 1400000 |  |  | $350,000/yr; Location? | 350000
TOTAL COST: CEAS |  |  | 0 | 1400000
6. Supportive Housing
Purchase/renovate for permanent housing |  |  |  | 1300000
Providing services |  |  |  | 0 |  |  | 4 year cost? Ongoing costs? | 0
TOTAL COST: SUPP. HOUSING |  |  | 0 | 1300000
7. Partial hospital care/ rehabilitative care/board and care
Providing services |  |  |  | 1040000 |  |  | $260,000/yr for 4 years; Location? | 260000
TOTAL COST: HOSPITAL CARE |  |  | 0 | 1040000
Totals for all 7 Programs: |  |  | 14133502.4 | 15725144.5 |  |  |  | 1881160 | 624237.4
Note: When the tax rate is lowered to (1/8)% after five years from (1/2)% for the first five years, this new rate will be 1/4 of the original rate. (1/8 is 1/4 of 1/2.) Thus, if we use projected annual tax proceeds of $7,250,000 , the ongoing Measure B monies would be 1/4 of this or $1,812,500 annually. This amount is close to the calculated amount of $1,881,160 in ongoing costs.
29858646.9
Additional Services/Operational Costs
Lee Kemper Report |  |  |  | 13011
Lee Kemper Report |  |  |  | 10282
Assessor Clerk Recorder - Election Costs |  |  |  | 161578
Lee Kemper Behavioral Needs Assessment |  |  |  | 14177
Sarah Riley consulting |  |  |  | 15694
Lee Kemper - Reimburse Executive Office |  |  |  | 27042
Office Expenses - Reimburse Executive Office |  |  |  | 257
CEO Labor and Benefits |  |  |  | 5207
Nash Gonzalez consulting |  |  |  | 8938
Verizon cell phone |  |  |  | 264
Fishman Supply Co - office supplies |  |  |  | 8
ATT Teleconference |  |  |  | 126
Laptop for Measure B |  |  |  | 1052
Measure B Salary and Benefits - A. Blair |  |  |  | 6517
Sonoma Media |  |  |  | 600
CDW GOVT and Granite Data -Pcard |  |  |  | 1214
GMR Transcription July - March 2020 |  |  |  | 1679
Facilities Salary and Benefits - Maintenance Training Ctr |  |  |  | 1760
Monthly Utilities - Repairs/Supplies Training Center |  |  |  | 1460
Measure B Salary and Benefits Alyson Bailey |  |  |  | 536000 | (4 yrs @$134K/yr)
806866
Total Allocated Measure B dollars by function: |  |  | 14133502.4 | 16532010.5
TOTAL MEASURE B DOLLARS ALLOCATED: |  |  |  | 30665512.9
|  |  | 46.09% | 53.91%
|  |  | Pct for Capital costs | Pct for Operations costs
REVENUES
|  | Maximum | Minimum
|  | 75% | 25%
TAX PROCEEDS (5 years) | Amount | Facilities | Operations
April 2018 to June 2018 | 1606571 | 1204929 | 401643
July 2018 to June 2019 | 8555373 | 6416529 | 2138843
July 2019 to June 2020 | 8647202 | 6485401 | 2161800
Projected July 2020 to June 2021
Projected July 2021 to June 2022
Projected July 2022 to March 2023
18809146
Quarterly Interest
Year 1 | 52500
Year 2 | 150000
Year 3 | 150000
Year 4 | 112500
Year 5 | 75000
540000
CHFA Grant | 500000 | [5 empty] | 38685146
777500
Annual Facilities Revenue | [6 empty] | 500000
Year 1 | 6052500 | [5 empty] | 345808
Year 2 | 6525000
Year 3 | 5900000 | [5 empty] | +
Year 4 | 5550000 | [5 empty] | 40308454
Year 5 | 7000000
31027500
| 17-18 actual (Apr-Jun ONLY) | 18-19 actual Year 1 (Jul-Jun) | 19-20 actual Year 2 (Jul-Jun) | 20-21 projected Year 3 (Jul-Jun) | 21-22 projected Year 4 (Jul-Jun) | 22-23 projected Year 5 Jul - Mar ONLY
TAX PROCEEDS (5 years) | 1606571 | 8555373 | 8647202 | 7000000 | 7251000 | 5625000
Quarterly Interest | 52500 | 150000 | 150000 | 200000 | 150000 | 75000
CHFA Grant |  |  | 500000
BHRTC Rental |  |  | 48448 | 73920 | 104160 | 119280
| 1659071 | 8705373 | 9345650 | 7273920 | 7505160 | 5819280
+
40308454
TOTAL MEASURE B EXPENSES ALLOCATED: | -30665512.9
TOTAL MEASURE B REVENUES: | 40308454
PROJECTED MEASURE B DOLLARS STILL AVAILABLE: | 9642941.1
Note: According to this financial analysis, a projected balance of $9,642,941 in Measure B dollars remains. The committee could consider building a second Crisis Residential Treatment facility in Ft. Bragg with this balance. According to the above figures, the total cost for a CRT is $7,387,626. This includes general operational costs for the next four years. There are options for a CRT that could be considered other than acquiring property and building from the ground up that could be less costly.

## the big picture revised
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
1. Crisis Residential Treatment (CRT)
Property Acquistion |  |  |  | 423000
Improvement Cost |  |  |  | 43000
CHFA Grant |  |  |  | -500000
-34000
Architecture and Design
Facility Planning and Progranning (Nacht and Lewis) |  |  |  | 89000
Design, Engineering and Criteria (Nacht and Lewis) |  |  |  | 567303
Special Consultants (Environmental/CEQA, BH Expert) |  |  |  | 58000
Geothechnical Investigation/Surveying |  |  |  | 35000
|  |  |  | subtotal > | 749303
Construction
Cupples base bid, site work portion |  |  |  | 1028000 |  |  | Total base bid:
Cupples base bid, construction portion |  |  | 1834000 |  |  |  | 2862000
Construction contingency (10% of base bid) |  |  | 64000 | 36000 |  |  | 64% to constr, 36% to site work |  | 100000
Additional construction contingency to meet 10% threshhold (10% of base bid less $100,000) |  |  | 119168 | 67032 |  |  | 64% to constr, 36% to site work |  | 186200
Cupples alternate 1 |  |  | 13100
Cupples alternate 2 |  |  | 31800
Cupples alternate 3 |  |  | 67965
Cupples alternate 4 |  |  | 50000
Cupples alternate 5 |  |  | 23000 |  |  |  | 0
Project escalation |  |  | 19444 | 19444 |  |  |  |  | 38888
|  | 2222477 | < subtotal | subtotal > | 1150476
Build/Support
Construction Manager (AECOM) |  |  |  | 332000 |  | a
Construction Management Contingency @15% |  |  |  | 49800 |  | *m |  |  | 49800
Building Commissioning |  |  |  | 59167 |  | b
Materials Testing (Construction) |  |  |  | 16271 |  | c
Plan Check and Permit Fees |  |  |  | 40000 |  | d
Utility Connections |  |  |  | 50000 |  | e
Advertising, Printing and Mailing |  |  |  | 10000 |  | f
Internal costs: County Staffing Cost-Facilities, Planning, etc. |  |  |  | 91325 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 100000 |  | *i
Other CEQA cost |  |  |  | 2500 |  | *j
City of Ukiah Address Change |  |  |  | 100 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 20000 |  | *l
Contingency (15% of Add't'l Construction costs |  |  |  | 115674.45 |  | g |  |  | 115476
|  |  |  | subtotal > | 886837.45
Ongoing Operations
General operational costs |  |  |  | 2000000 | 2000000 |  | Up to $500,000 annual cost for 4 years | 500000
TOTAL COST BY FUNCTION: CRT |  | 2222477 | 2222477 | 4752616.45 | 4752616.45 |  |  |  |  | subtotal
TOTAL COST: CRT |  |  | 6975093.45 | [6 empty] | 490364
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
2. Other Inpatient Psychiatric Care PHF Unit
Land acquisition |  |  |  | 500000 | 500000
Architecture and Design - Nacht and Lewis
Facility Planning and Progranning |  |  |  | 260000
PHF Design and Documentation |  |  |  | 1272750
PHF Construction Support |  |  |  | 522195
Special Consultants (Environmental/CEQA, Behavioral Health Expert) |  |  |  | 270000
Geothechnical Investigation/Surveying |  |  |  | 60000
Contingency 10% of Architecture and Design |  |  |  | 238496 |  |  |  |  | 238496
|  |  |  | subtotal > | 2623441
Construction
Construction |  |  | 9690000 |  |  |  | Remodel: number of beds?
Construction contingency 15% |  |  | 1453500 | [5 empty] | 1453500
|  | 11143500 | < subtotal
Build/Support
Construction Manager |  |  |  | 930031 |  | a
Construction Management Contingency @15% |  |  |  | 139504.65 |  | *m |  |  | 139505
Building Commissioning |  |  |  | 120000 |  | b
Materials Testing (Construction) |  |  |  | 93003 |  | c
Plan Check, Permit and Inspection Fees |  |  |  | 200000 |  | d
Utility Connections |  |  |  | 300000 |  | e
Advertising, Printing and Mailing |  |  |  | 5000 |  | f
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 0 |  | *h
Furnishings/Fixtures/Equipment |  |  |  | 0 |  | *i
Other CEQA cost |  |  |  | 0 |  | *j
City of Ukiah Address Change |  |  |  | 0 |  | *k
City of Ukiah Easement, Additional Fees |  |  |  | 0 |  | *l
Contingency 10% of Build/Support |  |  |  | 178754 |  |  |  |  | 178754
|  |  |  | subtotal > | 1966292.65
Ongoing Operations
General operational costs |  |  |  | TBD |  |  | Operational costs? | TBD |  | subtotal
TOTAL COST BY FUNCTION: PHF |  | 11143500 | 11143500 | 5089733.65 | 5089733.65 |  |  |  |  | 2010255
TOTAL COST: PHF |  |  | 16233233.65
Crisis Stabilization Unit (CSU) |  | not at this time
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
3. Behavioral Health Regional Training Center
Property Acquisition |  |  |  | 277957 | 277957 |  | Weer's report shows $274,457
Architecture and Design
Design/Engineering: plans and permits |  |  |  | 30000 | 30000
Construction/Remodel
General Remodel |  |  | 153900 |  |  |  | includes $4000 for septic repair
15% Contingency on General Remodel only |  |  | 23085 | [5 empty] | 23085
Replace ceiling fans |  |  | 568
Fencing |  |  | 3000
Fire Sprinklers |  |  | 60000
|  | 240553 | < subtotal
Build/Support
Testing/Inspections |  |  |  | 8500
Construction Manager |  |  |  | 34753
Start-up costs: Furnishing/Equipment |  |  |  | 24906
Other Internal Costs/Partners |  |  |  | 40000
|  |  |  | subtotal > | 108159
Ongoing Costs (budgeted to include 4 years of costs except for staffing)
Custodial |  |  |  | 30240 | at $42/hr; $630/mo | 630
Building Maintenance Mechanic |  |  |  | 26400 | at $55/hr; $550/mo | 550
Landscape Maintenance |  |  |  | 9216 | at $48/hr; $192/mo | 192
Utilities |  |  |  | 30240 |  | 630
Cost contingency for above 4 yrs at 13.85% |  |  |  | 13309.296 |  |  |  |  | 13309.296
Management (1 year only; effective 2023) |  |  |  | 46350 |  | 3862.5
Cost contingency for 1 yr management at 13.85% |  |  |  | 6419.475 |  |  |  |  | 6419.475
|  |  |  | subtotal > | 155755.296 | 5864.5 | < monthly cost
TOTAL COST BY FUNCTION: BHRTC |  | 240553 | 240553 | 571871.296 | 571871.296 |  | annual cost > | 70374
TOTAL COST: BHRTC |  |  | 812424.296
4. Expanded outreach/ Mobile Outreach Teams
|  |  |  | 1360000 |  |  | $340,000/yr for 4 years; Location/vehicles? | 340000
Providing Services |  |  |  | 1360000 |  |  | $340,000/yr for 4 years | 340000
Vehicles |  |  |  | TBD
Location: rent? |  |  |  | TBD
Strategic Plan: |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
TOTAL COST: MOBILE OUTREACH |  |  | 0 | 1360000
5. Community Education, Awareness, and Support (CEAS)
Providing services |  |  |  | 1400000 |  |  | $350,000/yr for 4 years | 350000
Location: rent? |  |  |  | TBD
TOTAL COST: CEAS |  |  | 0 | 1400000
6. Supportive Housing
Purchase/renovate for permanent housing |  |  |  | 1300000
Providing services |  |  |  | TBD |  |  | TBD | 0
TOTAL COST: SUPP. HOUSING |  |  | 0 | 1300000
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
7.Crisis Assessment and Psychiatric Hospitalization Aftercare
Providing services |  |  |  | 1040000 |  |  | $260,000/yr for 4 years | 260000
Location: rent? |  |  |  | TBD
TOTAL COST: HOSPITAL CARE |  |  | 0 | 1040000
Totals for all 7 Programs by function |  |  | 13606530 | 15514221.396 |  |  |  | 1860374 | 2543432.771
Note: When the tax rate is lowered to (1/8)% after five years from (1/2)% for the first five years, this new rate will be 1/4 of the original rate. (1/8 is 1/4 of 1/2.) Thus, if we use projected annual tax proceeds of $7,800,000 , the ongoing Measure B monies would be 1/4 of this or $1,950,000 annually. This amount would be sufficient to fund the calculated amount of $1,860,374 in ongoing costs identified thus far.
Total Allocated Measure B dollars by function: |  |  |  | 29120751.396
Additional Services/Operational Costs | Budgeted amt | Actual to date | Balance
Election: Assessor Clerk Recorder | 161578 | 161578 | 0
Kemper | 64512 | 64512 | 0
report: $13,011+$10,282 |  |  | 0
reimbursement executive office: $27,042 |  |  | 0
needs assessment: $14,177 |  |  | 0
Consulting |  |  | 0
Sarah Riley | 25000 | 15694 | 9306
Nash Gonzalez | 15000 | 8938 | 6062
Salaries |  |  | 0
Alyson Bailey | 316176 | 13104 | 303072 | $6587/mo x 48 mos (w adj) | 79044 | < annual cost
X. Ung | 187452 | 10414 | 177038 | $5207/mo x 36 mos | 62484 | < annual cost
141528
Bailey and Ung benefits (see [/ 381 om 20-21 Adopted Budget for BU 4052) | 178200
Miles | 12000 | 1009 | 10991
Miller | 50000 | 3919 | 46081
County Counsel | 5000 | 417 | 4583
Office related
cell phone | 2000 | 580 | 1420
supplies | 3000 | 2109 | 891
CDW | 6000 | 2761 | 3239
GMR transcription | 6500 | 1679 | 4821 | Jul - Mar 2020
Insurance
General liability annual | 1800 | 425 | 1375
Misc
Sonoma Media | 600 | 600 | 0
ATT Teleconference | 126 | 126 | 0
TOTAL: ADDITIONAL COSTS | 1034944 | 287865 | 747079
TOTAL MEASURE B DOLLARS ALLOCATED: |  |  |  | 30155695.396
|  |  | 45.12% | 54.88%
|  |  | Percent for Capital costs | Percent for Operations costs
REVENUES
|  | Maximum | Minimum
|  | 75% | 25%
TAX PROCEEDS (5 years) | Amount | Facilities | Operations
April 2018 to June 2018 | 1606571 | 1204929 | 401643
July 2018 to June 2019 | 8555373 | 6416529 | 2138843
July 2019 to June 2020 | 8647202 | 6485401 | 2161800
Projected July 2020 to June 2021
Projected July 2021 to June 2022
Projected July 2022 to March 2023
18809146
Quarterly Interest
Year 1 | 52500
Year 2 | 150000
Year 3 | 150000
Year 4 | 112500
Year 5 | 75000
540000
CHFA Grant | 500000 | [5 empty] | 39934146
777735
Annual Facilities Revenue | [6 empty] | #REF!
Year 1 | 6052500 | [5 empty] | 345808
Year 2 | 6525000
Year 3 | 5900000 | [5 empty] | +
Year 4 | 5550000 | [5 empty] | #REF!
Year 5 | 7000000
31027500
| 17-18 actual (Apr-Jun ONLY) | 18-19 actual Year 1 (Jul-Jun) | 19-20 actual Year 2 (Jul-Jun) | 20-21 projected Year 3 (Jul-Jun) | 21-22 projected Year 4 (Jul-Jun) | 22-23 projected Year 5 Jul - Mar ONLY |  | Totals
TAX PROCEEDS (5 years) | 1606571 | 8555373 | 8647202 | 8000000 | 7500000 | 5625000 |  | 39934146 | tax proceeds
Quarterly Interest | 17070 | 52500 | 183165 | 220000 | 200000 | 105000 |  | 777735 | interest
| 1623641 | 8607873 | 8830367 | 8220000 | 7700000 | 5730000 |  | 40711881
+
40711881
Projected BHRTC Rental |  |  | 48448 | 73920 | 104160 | 119280
TOTAL MEASURE B EXPENSES ALLOCATED: | -30155695.396
TOTAL MEASURE B REVENUES: | 40711881
PROJECTED MEASURE B DOLLARS STILL AVAILABLE: | 10556185.604
Note: According to this financial analysis, a projected balance of Measure B dollars remains. The committee could consider building a second Crisis Residential Treatment facility in Ft. Bragg with this balance. According to the above figures, the total cost for a CRT is $6,975,093. This includes general operational costs for the next four years. There are options for a CRT that could be considered other than acquiring property and building from the ground up that could be less costly.

## 12-12-21
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Budgeted Capital costs (Max 75%) | Budgeted Service or program/operational costs (Min 25%) | SUBTOTALS for Budgeted Operational costs | ACTUAL EXPENSES | BALANCE | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
1. Crisis Residential Treatment (CRT)
Property Acquistion |  |  |  | 423000 |  | 423000 | 0
Improvement Cost |  |  |  | 43000 |  |  | 43000
CHFA Grant |  |  |  | -500000 |  | -500000 | 0
-34000
A. ARCHITECTURE AND DESIGN - NACHT AND LEWIS
PREDESIGN
Site Analysis and Evaluation (determine site feasibility - phase 1) |  |  |  | 133000 |  | 128979.37 | 4020.63
CEQA Support (phase 1) |  |  |  | 35400 |  | 33444 | 1956
Geotechnical Investigation (phase 1); geotechnical scope for design level investigation of South Orchard Ave site only for the PHF); LACO Associates |  |  |  | 30800 |  | 19352.75 | 11447.25
Surveying (phase 1) |  |  |  | 15000 |  | 10000 | 5000
DESIGN AND CONSTRUCTION
Design and Documentation/Construction Support (phase 2) |  |  |  | 352913 |  | 342377.38 | 10535.62
Construction Administration |  |  |  | 158404 |  | 104820.32 | 53583.68
Contingency 10% (Bidding) |  |  |  | 63240 |  | 55486 | 7754
|  | N and L subtl |  |  | 788757 | 694459.82 | 94297.18
Sarah Riley consulting |  |  |  | 3390 | 3390 | 3390 | 0
B. CONSTRUCTION
Cupples base bid, site work portion |  |  |  | 758147 |  | 2842474.82 | 292290.18 | Total base bid:
Cupples base bid, construction portion |  |  | 2103853 |  |  |  |  | 2862000
Construction contingency (10% of base bid) |  |  | 64000 | 36000 |  |  |  | 64% to constr, 36% to site work |  | 100000
Additional construction contingency to meet 10% threshhold (10% of base bid less $100,000) |  | Contract amount $3,134,765 | 119168 | 67032 |  | 0 | 186200 | 64% to constr, 36% to site work |  | 186200
Cupples alternate 1 (listed As $13,100 in contract) |  | Green= | 0
Cupples alternate 2 |  | 3134765 | 31800
Cupples alternate 3 |  |  | 67965
Cupples alternate 4 |  |  | 50000
Cupples alternate 5 |  |  | 23000 |  |  |  |  | 0
Project escalation |  |  | 19444 | 19444 |  | 0 | 38888 |  |  | 38888
|  | 2479230 | < subtotal | subtotal > | 880623
C. BUILD/SUPPORT
Construction Manager (AECOM) | Contract amount $331,738 |  |  | 331738 |  | 187409.51 | 144328.49
LACO |  |  |  | 45800 |  | 16229.89 | 29570.11
Construction Management Contingency @15% |  |  |  | 49760.7 |  | 0 | 49760.7 |  |  | 49800
Phillips Seabrook |  |  |  | 3105 |  | 4804.57 | -1699.57
Redwood Empire Title |  |  |  | 400 |  | 400 | 0
Building Commissioning |  |  |  | 59167 |  | 0 | 59167
Plan Check and Permit Fees |  |  |  | 40000 |  | 0 | 40000
Utility Connections |  |  |  | 50000 |  | 20429.98 | 29570.02
Advertising, Printing and Mailing |  |  |  | 10000 |  | 0 | 10000
Internal costs: County Staffing Cost-Facilities, Planning, etc. |  |  |  | 91325 |  | 0 | 91325
Furnishings/Fixtures/Equipment |  |  |  | 100000 |  | 0 | 100000
Ukiah Valley Fire |  |  |  | 900 |  | 900 | 0
UVSD |  |  |  | 15438 |  | 15337.2 | 100.8
City of Ukiah Easement, Additional Fees |  |  |  | 20000 |  | 0 | 20000
Contingency (15% of Add't'l Construction costs |  |  |  | 115674.45 |  | 0 | 115674.45 |  |  | 115476
|  | subtotal > |  |  | 933308.15
0
SONOMA SWEEPERS |  |  |  | 463 |  | 462 | 1
PROJ CA001 |  |  |  | 17911 | 18374 | 17910.9 | 0.1
D. ONGOING OPERATIONS | [6 empty] | 0
General operational costs |  |  |  | 2000000 | 2000000 | 0 | 2000000 | Up to $500,000 annual cost for 4 years | 500000
TOTAL COST BY FUNCTION: CRT |  | 2479230 | 2479230 | 4590452.15 | 4590452.15 | 3727208.69 | 3342473.46 |  |  |  | cont's subtotal
TOTAL COST: CRT |  |  | 7069682.15 | [7 empty] | 490364
7069682.15
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Budgeted Capital costs (Max 75%) | Budgeted Service or program/operational costs (Min 25%) | SUBTOTALS for Budgeted Operational costs | ACTUAL EXPENSES | BALANCE | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
2. Other Inpatient Psychiatric Care PHF Unit
Land acquisition |  |  |  | 500000 | 500000 | 0
A. ARCHITECTURE AND DESIGN - NACHT AND LEWIS
PREDESIGN
Whitmore Land PHF Study |  |  |  | 104830 |  | 71938 | 32892
DESIGN AND CONSTRUCTION (assumes new construction of approximately 16,000 GSF) | [6 empty] | 0
Design and Documentation - phase 3 |  |  |  | 1272750 |  | 0 | 1272750
Construction Support - phase 3 |  |  |  | 522195 |  | 0 | 522195
Contingency 10% of Architecture and Design |  |  |  | 192794.5 |  | 0 | 192794.5 |  |  | 192794.5
|  |  |  | subtotal > | 2092569.5 |  | #VALUE!
B. CONSTRUCTION | [6 empty] | 0
Construction |  |  | 9690000 |  |  | 0 | 0 | Remodel: number of beds?
Construction contingency 15% |  |  | 1453500 |  |  | 0 | 0 |  |  | 1453500
|  | 11143500 | < subtotal
C. BUILD/SUPPORT
Construction Manager |  |  |  | 930031 |  | 0 | 930031
Construction Management Contingency @15% |  |  |  | 139504.65 |  | 0 | 139504.65 |  |  | 139505
Building Commissioning |  |  |  | 120000 |  | 0 | 120000
Materials Testing (Construction) |  |  |  | 93003 |  | 0 | 93003
Plan Check, Permit and Inspection Fees |  |  |  | 200000 |  | 0 | 200000
Utility Connections |  |  |  | 300000 |  | 0 | 300000
Advertising, Printing and Mailing |  |  |  | 5000 |  | 0 | 5000
County Staffing Cost-Facilities, Planning, etc. |  |  |  | 0 |  | 0 | 0
Furnishings/Fixtures/Equipment |  |  |  | 0 |  | 0 | 0
Other CEQA cost |  |  |  | 0 |  | 0 | 0
City of Ukiah Address Change |  |  |  | 0 |  | 0 | 0
City of Ukiah Easement, Additional Fees |  |  |  | 0 |  | 0 | 0
Contingency 10% of Build/Support |  |  |  | 178754 |  | 0 | 178754 |  |  | 178754
|  |  |  | subtotal > | 1966292.65
D. ONGOING OPERATIONS
General operational costs |  |  |  | TBD |  |  |  | Operational costs? | TBD |  | cont's subtotal
TOTAL COST BY FUNCTION: PHF |  | 11143500 | 11143500 | 4558862.15 | 4558862.15 | [5 empty] | 1964553.5
TOTAL COST: PHF |  |  | 15702362.15
3. Crisis Stabilization Unit (CSU)
A. ARCHITECTURE AND DESIGN - NACHT AND LEWIS
PREDESIGN
Site Analysis and Evaluation (determine site feasibility - phase 1) |  |  |  | 133000
DESIGN AND CONSTRUCTION (assumes new construction of approximately 4,000 GSF)
Design and Documentation - phase 3 |  |  |  | 254550
Construction Support - phase 3 |  |  |  | 104440
Contingency 10% of Architecture and Design |  |  |  | 49199 | [5 empty] | 49199
|  |  |  | subtotal > | 541189
B. CONSTRUCTION (cost for the PHF x 25%)
Cost |  |  | 2422500
15% ConstructionContingency |  |  | 363375 | [6 empty] | 363375
|  | 2785875 | < subtotal
C. BUILD/SUPPORT (cost for the PHF x 25%)
Construction Manager |  |  |  | 232507.75
Construction Management Contingency @15% |  |  |  | 34876.1625 | [5 empty] | 34876.1625
Other |  |  |  | 179500.75
Contingency 10% of other Build/Support |  |  |  | 17950.075 | [5 empty] | 17950.075
D. ONGOING OPERATIONS |  |  |  |  | 464834.7375
General operational costs |  |  |  | TBD |  |  |  | Operational costs? | TBD
TOTAL COST BY FUNCTION: CSU |  | 2785875 | 2785875 | 1006023.7375 | 1006023.7375
TOTAL COST: CSU |  |  | 3791898.7375
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Budgeted Capital costs (Max 75%) | Budgeted Service or program/operational costs (Min 25%) | SUBTOTALS for Budgeted Operational costs | ACTUAL EXPENSES | BALANCE | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
4. Behavioral Health Regional Training Center
Property Acquisition |  |  |  | 277957 | 277957 |  |  | Weer's report shows $274,457
Architecture and Design
Design/Engineering: plans and permits |  |  |  | 30000 | 30000
Construction/Remodel
General Remodel(see BOS 1-26-21 presentation) Adams Construction |  | Contract amount $295,858 | 168267 |  |  |  |  | includes $4000 for septic repair
15% Contingency on General Remodel only |  |  | 25240.05 | [6 empty] | 25240.05
Replace ceiling fans |  |  | 568
Fencing |  |  | 3000
LED Lighting (approved by Meas B OC at 1-27-21 mtg) |  |  | 19154
Fire Sprinklers (not approved by Meas B OC at 1-27-21 mtg) |  |  | 0
Other (to match contract amount) |  |  | 79629
|  | 295858.05 | < subtotal
Build/Support
Testing/Inspections |  |  |  | 8500
Construction Manager |  |  |  | 34753
Start-up costs: Furnishing/Equipment |  |  |  | 24906
Other Internal Costs/Partners |  |  |  | 40000
|  |  |  | subtotal > | 108159
Ongoing Costs (budgeted to include 4 years of costs except for staffing)
Custodial at $42/hr; $630/mo |  |  |  | 30240 | at $42/hr; $630/mo
Building Maintenance Mechanic at $55/ht; $550/mo |  |  |  | 26400 | at $55/hr; $550/mo
Landscape Maintenance at $48/hr; $`92/m0 |  |  |  | 9216 | at $48/hr; $192/mo
Utilities at $630/mo |  |  |  | 30240
Cost contingency for above 4 yrs at 13.85% |  |  |  | 13309.296 | [5 empty] | 13309.296
Management (1 year only; effective 2023); at $3,862.50/mo |  |  |  | 46350
Cost contingency for 1 yr management at 13.85% |  |  |  | 6419.475 | [5 empty] | 6419.475
|  |  |  | subtotal > | 155755.296
TOTAL COST BY FUNCTION: BHRTC |  | 295858.05 | 295858.05 | 571871.296 | 571871.296
TOTAL COST: BHRTC |  |  | 867729.346
5. Expanded outreach/ Mobile Outreach Teams
|  |  |  | 1360000 |  |  |  | $340,000/yr for 4 years; Location/vehicles? | 340000
Providing Services |  |  |  | 1360000 |  |  |  | $340,000/yr for 4 years | 340000
Vehicles |  |  |  | TBD
Location: rent? |  |  |  | TBD
Strategic Plan: |  | SUBTOTALS for Capital costs | Capital costs (Max 75%) | Service or program/operational costs (Min 25%) | SUBTOTALS for Operational costs |  |  | Notes/Questions | other annual ongoing costs after expected reimbursements | TOTAL of Contingencies
TOTAL COST: MOBILE OUTREACH |  |  | 0 | 1360000
6. Community Education, Awareness, and Support (CEAS)
Providing services |  |  |  | 1400000 |  |  |  | $350,000/yr for 4 years | 350000
Location: rent? |  |  |  | TBD
TOTAL COST: CEAS |  |  | 0 | 1400000
7. Mendocino Coast Crisis Respite Program
Service provided by Redwood Community Services (RCS) | [7 empty] | Funded through additional funding streams including grants to sustaim program long term
Cost to Measure B is $240,000/yr |  |  |  | 960000
TOTAL COST: CEAS |  |  | 0 | 960000
8. Supportive Housing
Purchase/renovate for permanent housing |  |  |  | 1300000
Providing services |  |  |  | TBD |  |  |  | TBD | 0
TOTAL COST: SUPP. HOUSING |  |  | 0 | 1300000
Measure B Expenditure Plan as it Connects to the Strategic Plan |  | SUBTOTALS for Capital costs | Budgeted Capital costs (Max 75%) | Budgeted Service or program/operational costs (Min 25%) | SUBTOTALS for Budgeted Operational costs | ACTUAL EXPENSES | BALANCE | Notes/Questions | other annual ongoing costs after expected reimbursements | Contingencies
9. Crisis Assessment and Psychiatric Hospitalization Aftercare
Providing services |  |  |  | 1040000 |  |  |  | $260,000/yr for 4 years | 260000
Location: rent? |  |  |  | TBD
TOTAL COST: HOSPITAL CARE |  |  | 0 | 1040000
NAMI Contract over 4 years |  |  |  | 700000
Crisis Intervention Training 12/1-12/3, 2021 |  |  |  | 13000
Totals for all Programs by function |  |  | 16704463.05 | 17500209.3335 |  |  |  |  | 1790000 | 2965286.5585
Note: When the tax rate is lowered to (1/8)% after five years from (1/2)% for the first five years, this new rate will be 1/4 of the original rate. (1/8 is 1/4 of 1/2.) Thus, if we use projected annual tax proceeds of $8,000,000 , the ongoing Measure B monies would be 1/4 of this or $2,000,000 annually. This amount would short to fund the identified calculated amount of $2,120,374 in ongoing costs identified thus far.
Total Allocated Measure B dollars by function: |  |  |  | 34204672.3835
Additional Services/Operational Costs | Actuals through 6/30/20
Election: Assessor Clerk Recorder | 161578 |  |  |  | 31389
Kemper | 64769 |  |  |  | 0
13011 |  | report
10282 |  | report
27299 |  | reimburse executive office
14177 |  | needs assessment (included in April to July 2018) | [6 empty] | Riley | Gonzalez | Verizon |  | Laptop |  | Ung/Blair
64769 |  |  |  | 199048 |  |  |  |  | 1440 | 7063 | 50 |  | 1052 |  | 2986
Consulting | [8 empty] | 400 | 1875 | 25 |  |  |  | 2221
Sarah Riley 18/19 | 4090 | [7 empty] | 1560 | 8938 | 46 |  |  |  | 5384
Sarah Riley 19/20 | 11604 | [7 empty] | 690
Sarah Riley (amount charged to CRT); included in CRT budget | -3390
Nash Gonzalez | 8938 | [9 empty] | 77 |  |  |  | 1133
Salaries | [8 empty] | 1740 |  | 66 |  | Facilities Salary/Benefits |  | 11724
Alyson Bailey | [8 empty] | 540 | CDW | 264 |  | 1760
X. Ung/Blair | 11724 | [7 empty] | 2700 | 1214
[9 empty] | 1800 | 8 |  |  | Utilities BHRTC
[9 empty] | 1320 | 1222 |  |  | 1460
Miles | 0 | [7 empty] | 480
Miller/Miles | 0 | [7 empty] | 1320
County Counsel | 0 | [7 empty] | 864
Facilities Salaries/Benefits-Maintenance Training Ctr | 1760 | [7 empty] | 840
15694
Office related
Verizon | 264
supplies | 1052 | [7 empty] | April to July 2018 | July 2018 to June 2019 | Jul 2019 to June 2020
CDW | 1222 | [7 empty] | 199048 | 31389 | 581056 |  | 811493
GMR transcription | 1679 | Jul - Mar 2020
40429
Utilities | [10 empty] | 274457 | Purchase Training Facility |  | DNI here
BHRTC | 1460 | [9 empty] | 39228 | Cost to date: BHRTC |  | DNI here
Misc | [10 empty] | 226942 | Cost to date: CRT |  | DNI here
Sonoma Media | 600 | [9 empty] | 581056
ATT Teleconference | 126
TOTAL COSTS through June 2019 | 267476
Fiscal Year |  | 20/21 | 0.95455 |  | 22/23 projected
Salaries |  | 93739 |  | 134556
Bailey | 90181
Communications |  | 646 |  | 500
General Liability Insurance |  | 425 |  | 358
Office Supplies |  | 2616 |  | 2000
Education and Training |  | 0 |  | 1000
Prof and Spec Svcs-Other |  | 0 |  | 610000
Public and Legal Notices |  | 0 |  | 500
A-87 Costs |  | 0 |  | 20000
Info Tech Equipment |  | 599 |  | 3337
Special Dept Exp |  | 66316 |  | 388549
Ung | 3805
K. Miles | 4097
L. Chavoya | 1795
J. Miller | 2689
K. Lovato | 13991
A.Turchin | 2000
J. Beeler | 5951
D. Thompson | 477
S. Smallcombs (MCRU) | 18012
(sum of salaries in 20/21):
142998
County Counsel | 2822
Sonoma Sweepers | 2817
PreEmp Screen | 160
CIT Training | 11730
Travel In-County |  | 336 |  | 500
Travel Out-of-County |  | 0 |  | 1000
Mental Health Treatment Act Audit |  |  |  | 6000
TOTAL COSTS ACTUAL (20/21)AND BUDGETED (21/22): DOES NOT INCLUDE INDIVIDUAL PROJECT COSTS |  | 164677 |  | 1168300 | 1000000
Total of Non-Project-Specific Costs: |  | 2600453
TOTAL MEASURE B DOLLARS ALLOCATED: |  |  |  | 36805125.3835
|  |  | 45.39% | 48.28%
|  |  | Percent for Capital costs | Percent for Operations costs
REVENUES
|  | Maximum | Minimum
|  | 75% | 25%
TAX PROCEEDS (5 years) | Amount | Facilities | Operations
April 2018 to June 2018 | 1606571 | 1204929 | 401643
July 2018 to June 2019 | 8555373 | 6416529 | 2138843
July 2019 to June 2020 | 8647202 | 6485401 | 2161800
Projected July 2020 to June 2021
Projected July 2021 to June 2022
Projected July 2022 to March 2023
18809146
Quarterly Interest
Year 1 | 52500
Year 2 | 150000
Year 3 | 150000
Year 4 | 112500
Year 5 | 75000
540000
CHFA Grant | 500000 | [6 empty] | 42824000
723015
Annual Facilities Revenue | [7 empty] | #REF!
Year 1 | 6052500 | [6 empty] | 226528
Year 2 | 6525000
Year 3 | 5900000 | [6 empty] | +
Year 4 | 5550000 | [6 empty] | #REF!
Year 5 | 7000000
31027500
| 17-18 actual (Apr-Jun ONLY) | 18-19 actual Year 1 (Jul-Jun) | 19-20 actual Year 2 (Jul-Jun) | 20-21 actual Year 3 (Jul-Jun) | 21-22 projected Year 4 (Jul-Jun) | 22-23 projected Year 5 Jul - Mar ONLY | Totals
TAX PROCEEDS (5 years) | 1606571 | 8555373 | 8647202 | 10014854 | 8000000 | 6000000 | 42824000 | revenue fr sales tax
Quarterly Interest | 17070 | 52500 | 183165 | 207780 | 150000 | 112500 | 723015 | revenue fr interest
| 1623641 | 8607873 | 8830367 | 10222634 | 8150000 | 6112500 | 43547015
Projected BHRTC Rental |  |  | 48448 | 73920 | 104160
TOTAL MEASURE B EXPENSES ALLOCATED: | -36805125.3835
TOTAL MEASURE B REVENUES: | 43547015
PROJECTED MEAS B DOLLARS STILL AVAILABLE: | 6741889.6165